## TEST PLAN
HRMS TEST PLAN
FEATURES TO BE TESTED (IN-SCOP) | ESTIMATION
*Dashboard *Document *Contact | *Dashboard *Document: 6 hr *Contact
FEATURES NOT TO BE TESTED | STAFING AND TRAINING
* Edit Contact Information | Staffing * Manual Tester: 2 * Automation Tester: 2 Training * Swostitechsolutions: 16 hours
TEST LEVELS AND TEST TYPES | ASSUMPTIONS
Test Levels * System Testing * Acceptance Testing Test Types * Functional Testing * Usability Testing * performance testing *compartibility Testing *Regression Testing | * Developers (Backend + Frontend) deliver the code related to the features * License for Swostitech Solutions
EXIT CRITERIA | RISKS
* Testing is finished and there are no functional bugs * All remaining bugs have low seviority * No more than 10% of medium-seviority bugs are open | List of Risks * Risk 1 = Late Delivery for Features * Risk 2 = QA Environment is down * Risk 3 = Un-planned vacations * Risk 4 = Critical Bugs keeps showing which affects the time frame Risk Mitigation * Risk 1 = Risk Acceptance * Risk 2 = Risk Transfer * Risk 3 = Risk Monitoring * Risk 4 = Risk Acceptance
SUSPENSION CRITERIA | TEST REFERENCES
* Critical Bugs are open and they are blocking testing * All remaing test cases are blocked by an open bug | * User Stories * System Design
TEST DELIVERABLE
* Test cases * Bugs Report * Test Summary Report
TEST ENVIRONMENT
* Operating system: Windows 10 * Server: Swostitech Soluction * Browser: Google Crome * Network: Wi-Fi

## LOGIN
LAW FIRM APPLICATION
[5 empty] | URL: | http://52.66.66.205:5069/#
[5 empty] | Created and Executed By: | Biswalaxmi Nayak
TC_ID | TEST SCENARIOS | TEST DESCRIPTION | INPUT DATA | STEPS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | PRIORITY | SEVIORITY

## DOCUMENT
http://52.66.66.205:5069/#
| TC_ID | TEST SCENARIOS | TEST DESCRIPTION | INPUT DATA | STEPS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | PRIORITY | SEVIORITY
| TC_01 | To verify DOCUMENT button is enable | Verify DOCUMENT button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Verify Enability | 1. DOCUMENT button should be Enable | 1. DOCUMENT button is Enable | Pass | P0 | S0
| TC_02 | To verify DOCUMENT button is functioning | Verify DOCUMENT button is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Verify Functionality | 1. DOCUMENT button should be Function and open DOCUMENT page | 1. DOCUMENT button is working | Pass | P0 | S0
| TC_03 | To verify NEW button is enable | Verify NEW button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Press Enter key 6. click on NEW button 7.Verify Enability | 1. NEW button should be Enable | 1. NEW button is Enable | Pass | P0 | S0
| TC_04 | To verify NEW button is enable | Verify NEW button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Press Enter key 6. click on NEW button 7.Verify Functionality | 1. NEW button should be Function and open ADD DOCUMENT page | 1. NEW button is working and opening ADD DOCUMENT page | Pass | P0 | S0
| TC_05 | To verify EXIT button is enable | Verify EXIT button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Press Enter key 6. click on EXIT button 7.Verify Enability | 1. EXIT button should be Enable | 1. EXIT button is Enable | Pass | P0 | S0
| TC_06 | To verify EXIT button is enable | Verify EXIT button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Press Enter key 6. click on EXIT button 7.Verify Functionality | 1. EXIT button should be Function and CLOSE the DOCUMENT page | 1. EXIT button is working and CLOSEING the DOCUMENT page | Pass | P0 | S0
ADD DOCUMENT PAGE | TC_07 | To verify EXIT button of ADD DOCUMENT page is enable | Verify EXIT button of ADD DOCUMENT page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6. click on EXIT button 7.Verify Enability | 1. EXIT button of ADD DOCUMENT page should be Enable | 1. EXIT button of ADD DOCUMENT page is Enable | Pass | P0 | S0
| TC_08 | To verify EXIT button of ADD DOCUMENT page is functioning | Verify EXIT button of ADD DOCUMENT page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6. click on EXIT button 7.Verify Functionality | 1. EXIT button of ADD DOCUMENT page should be Function and CLOSE the ADD DOCUMENT page | 1. EXIT button of ADD DOCUMENT page is working and CLOSEING the ADD DOCUMENT page | Pass | P0 | S0
| TC_09 | To verify ADD button is enable | Verify ADD button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6. Press ADD button 7. Verify Enability | 1. ADD button should be Enable | 1. ADD button is Enable | Pass | P0 | S0
| TC_10 | To verify ADD button is Functioning with valid data | Verify ADD button is Functioning with valid data | Case id=A Name= B Document Details= C Date= 13/09/2023 | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6. Enter Case id=A Name= B Document Details= C Date= 13/09/2023 7. Press ADD button 7. Verify Functionality | 1. ADD button should add the data and shows msg as: successfully added | 1. ADD button adds the data and shows msg as: successfully added | Pass | P0 | S0
| TC_11 | To verify CANCEL button is enable | Verify CANCEL button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 7. Press CANCEL button 7. Verify Enability | 1. CANCEL button should be Enable | 1. CANCEL button is Enable | Pass | P0 | S0
| TC_12 | To verify CANCEL button is functioning | Verify CANCEL button is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 7. Press CANCEL button 7. Verify Functionality | 1. CANCEL button should be Function and close the ADD DOCUMENT page | 1. CANCEL button is working and close the ADD DOCUMENT page | Pass | P0 | S0
| TC_13 | To verify CASE ID field is Enability | Verify CASE ID field is Enability |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CASE ID field 7. Verify Enability | CASE ID field should Enable and allow to enter Data | CASE ID field is Enable and allows to enter Data | Pass | P0 | S0
| TC_14 | To verify CASE ID field Function(+ve test) | Verify CASE ID field Function(+ve test) | Case id=Abc123 | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CASE ID field 7. Enter Case id= Abc123 8. Press ADD button 9.Verify Functionality | Pressing ADD button CASE ID field should Show the id = Abc123 without any Error | Pressing ADD button CASE ID field Shows the id = Abc123 without any Error | Pass | P0 | S0
| TC_15 | To verify CASE ID field Function with an invalid data(-ve test) | Verify CASE ID field Function with an invalid data(-ve test) | Case id=Abc123@ # | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CASE ID field 7. Enter Case id= Abc123@ # 8. Press ADD button 9.Verify Functionality | Pressing ADD button CASE ID field should Show the id = Abc123@ # with an Error msg as: Case ID must be alphanumeric and may contain /, _, and - with a maximum length of 16 characters | Pressing ADD button CASE ID field Shows the id = Abc123@ # with an Error msg as: Case ID must be alphanumeric and may contain /, _, and - with a maximum length of 16 characters | Pass | P0 | S0
| TC_16 | To verify CASE ID field Function with blank space(-ve test) | Verify CASE ID field Function blank space(-ve test) | Case id=-------- | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CASE ID field 7. Enter Case id= ------- 8. Press ADD button 9.Verify Functionality | Pressing ADD button CASE ID field should Shows an Error msg as: Case ID is required | Pressing ADD button CASE ID field Shows an Error msg as: Case ID is required | Pass | P0 | S0
| TC_17 | To verify NAME field is Enability | Verify NAME field is Enability |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on NAME field 7. Verify Enability | NAME field should Enable and allow to enter Data | NAME field is Enable and allows to enter Data | Pass | P0 | S0
| TC_18 | To verify NAME field Function(+ve test) | Verify NAME field Function(+ve test) | NAME=Abc | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on NAME field 7. Enter NAME= Abc 8. Press ADD button 9.Verify Functionality | Pressing ADD button NAME field should Show the id = Abc without any Error | Pressing ADD button NAME field Shows the id = Abc without any Error | Pass | P0 | S0
| TC_19 | To verify NAME field Function with an invalid data(-ve test) | Verify NAME field Function with an invalid data(-ve test) | NAME =Abc123 @ | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on NAME field 7. Enter NAME= Abc123 @ 8. Press ADD button 9.Verify Functionality | Pressing ADD button NAME field should Show the id = Abc123 @ with an Error msg as: Name must contain only alphabetic characters and be at most 25 characters long | Pressing ADD button NAME field Shows the id = Abc123@ # with an Error msg as: Name must contain only alphabetic characters and be at most 25 characters long | Pass | P0 | S0
| TC_20 | To verify NAME field Function with blank space(-ve test) | Verify NAME field Function blank space(-ve test) | NAME=-------- | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on NAME field 7. Enter NAME= ------- 8. Press ADD button 9.Verify Functionality | Pressing ADD button NAME field should Shows an Error msg as: Name is required | Pressing ADD button NAME field Shows an Error msg as: Name is required | Pass | P0 | S0
| TC_21 | To verify DOCUMENT DETAILS field is Enability | Verify DOCUMENT DETAILS field is Enability |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DOCUMENT DETAILS field 7. Verify Enability | DOCUMENT DETAILS field should Enable and allow to enter Data | DOCUMENT DETAILS field is Enable and allows to enter Data | Pass | P0 | S0
| TC_22 | To verify DOCUMENT DETAILS field Function | Verify DOCUMENT DETAILS field Function |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DOCUMENT DETAILS field 7. Enter data 8. Press ADD button 9.Verify Functionality | Pressing ADD button DOCUMENT DETAILS field should Show the entered data without any Error | Pressing ADD button DOCUMENT DETAILS field Shows the entered data without any Error | Pass | P0 | S0
| TC_23 | To verify DOCUMENT DETAILS field Function with blank space(-ve test) | Verify DOCUMENT DETAILS field Function blank space(-ve test) | DOCUMENT DETAILS=-------- | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on NAME field 7. Enter DOCUMENT DETAILS= ------- 8. Press ADD button 9.Verify Functionality | Pressing ADD button DOCUMENT DETAILS field should Shows an Error msg as: Document Details is required | Pressing ADD button DOCUMENT DETAILS field Shows an Error msg as: Document Details is required | Pass | P0 | S0
| TC_24 | To verify DATE field is Enability | Verify DATE field is Enability |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DATE field 7. Verify Enability | DATE field should Enable and allow to enter Data | DATE field is Enable and allows to enter Data | Pass | P0 | S0
| TC_25 | To verify DATE field Function with valid date(+VE TEST) | Verify DATE field Function with valid date(+VE TEST) | DATE= 13/09/2023 | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DATE field 7. Enter DATE=13/09/2023 8. Press ADD button 9.Verify Functionality | Pressing ADD button DATE field should Show the entered data13/09/2023without any Error | Pressing ADD button DATE field Shows the entered data =13/09/2023 without any Error | Pass | P0 | S0
| TC_26 | To verify DATE field Function with invalid date(-VE TEST) | Verify DATE field Function with invalid date(-VE TEST) | DATE= 31/12/5201 | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DATE field 7. Enter DATE=31/12/5201 8. Press ADD button 9.Verify Functionality | Pressing ADD button data should not added and show an Error msg:REQUIRED VALID DATE | Dta is adding successfully without any Error msg | Fail | P0 | S0
| TC_27 | To verify DATE field Function with blank space(-VE TEST) | Verify DATE field Function with blank space(-VE TEST) | DATE= ------- | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on DATE field 7. Enter DATE=----- 8. Press ADD button 9.Verify Functionality | Pressing ADD button DATE field should Show show an Error msg:Date is required | Pressing ADD button DATE field Shows an Error msg:Date is required | Pass | P0 | S0
| TC_28 | To verify CALENDAR is Enability | Verify CALENDAR is Enability |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CALENDAR field 7. Verify Enability | CALENDAR field should Enable | CALENDAR field is Enable | Pass | P0 | S0
| TC_29 | To verify CALENDAR is Functioning | Verify CALENDAR is Functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CALENDAR field 7. Verify Functionality | CALENDAR field should Enable and allow toselect the date | CALENDAR field is Enable and allows to select the date | Pass | P0 | S0
| TC_30 | To verify CALENDAR is Functioning with future data (-ve test) | Verify CALENDAR is Functioning with future data (-ve test) | DATE= 13/02/99999 | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEW button 6.click on CALENDAR field 7. enter date=13/02/999999 8. Verify Functionality | DATE field should not allow invalid date show an error msg as: invalid date | DATE field allows invalid date with out anyerror msg | Fail | P0 | S0
| TC_31 | To verify SEARCH button is enable | Verify SEARCH button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on SEARCH button 6. Verify Enability | 1. SEARCH button should be Enable | 1. SEARCH button is Enable | Pass | P0 | S2
| TC_32 | To verify SEARCH button is Functioning with valid data(+ VE TEST) | Verify SEARCH button is Functioning with valid data(+ VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on SEARCH button 6. Enter a valid data(which id or name is recorded in page) 7. press Enter 8. Verify functionality | By pressing search button result should be shown | By pressing search button result is showing | Pass | P0 | S0
| TC_33 | To verify SEARCH button is Functioning with invalid data(- VE TEST) | Verify SEARCH button is Functioning with invalid data(-VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on SEARCH button 6. Enter a invalid data(which id or name is is not available in page) 7. press Enter 8. Verify functionality | By pressing search button result should be shown as : No data available | By pressing search button result is showing as: No data available | Pass | P0 | S0
| TC_34 | To verify FILTER BY YEAR button is enable | Verify FILTER BY YEAR button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on FILTER BY YEAR button 6. Verify Enability | 1. FILTER BY YEAR button should be Enable | 1. FILTER BY YEAR button is Enable | Pass | P0 | S2
| TC_35 | To verify FILTER BY YEAR button is Functioning with valid data(+ VE TEST) | Verify FILTER BY YEAR button is Functioning with valid data(+ VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on FILTER BY YEAR button 6. Enter a valid year(which year is recorded in page) 7. press Search button 8. Verify functionality | By pressing search button result should be shown | By pressing search button result is showing | Pass | P0 | S0
| TC_36 | To verify FILTER BY YEAR button is Functioning with invalid data(- VE TEST) | Verify FILTER BY YEAR button is Functioning with valid data(-VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on FILTER BY YEAR button 6. Enter a invalid year(which year is notrecorded in page) 7. press Search button 8. Verify functionality | By pressing search button result should be shown as : No data available | By pressing search button result is showing as: No data available | Pass | P0 | S0
| TC_37 | To verify ENTER KEY is Functioning in FILTER BY YEAR button from keyboard | Verify ENTER KEY is Functioning in FILTER BY YEAR button from keyboard |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on FILTER BY YEAR button 6. Enter a year 7. press ENTER KEY from keyboard 8. Verify functionality | By pressing ENTER KEY from keyboard should work and result should be shown | By pressing ENTER KEY from keyboard is not working and not showing any result | Fail | P1 | S1
| TC_38 | To verify PREVIOUS BUTTON is enable | Verify PREVIOUS BUTTON is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on PREVIOUS BUTTON 6.Verify Enability | PREVIOUS BUTTON should enable | PREVIOUS BUTTON is enable | Pass | P0 | S0
| TC_39 | To verify PREVIOUS BUTTON is functioning | Verify PREVIOUS BUTTON is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on PREVIOUS BUTTON 6.Verify functionality | PREVIOUS page should be open | PREVIOUS page is opening | Pass | P0 | S0
| TC_40 | To verify NEXT BUTTON is enable | Verify NEXT BUTTON is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEXT BUTTON 6.Verify Enability | NEXT BUTTON should enable | NEXT BUTTON is enable | Pass | P0 | S0
| TC_41 | To verify NEXT BUTTON is functioning | Verify NEXT BUTTON is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on NEXT BUTTON 6.Verify functionality | NEXT page should be open | NEXT page is opening | Pass | P0 | S0
| TC_42 | To verify COUNT PER PAGE DROP DOWN BUTTON is enable | Verify COUNT PER PAGE DROP DOWN BUTTON is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on COUNT PER PAGE DROP DOWN BUTTON 6.Verify Enability | DROP DOWN button should be Enable | DROP DOWN button is enable | Pass | P0 | S0
| TC_43 | To verify COUNT PER PAGE DROP DOWN BUTTON is functioning | Verify COUNT PER PAGE DROP DOWN BUTTON is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on COUNT PER PAGE DROP DOWN BUTTON 6.Verify functionality | DROP DOWN button should be function and show the correct count in page | DROP DOWN button functions and shows the correct count in page | Pass | P0 | S0
CASE ID LINK AND PAGE | TC_44 | To verify To verify the CASE ID LINK is functioning | Verify To verify the CASE ID LINK is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6.Verify functionality | Document page of that CASE ID should be open | Document page of that CASE ID is opening | Pass | P0 | S0
| TC_45 | To verify EXIT button of page is enable | Verify EXIT button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. click on EXIT button 7.Verify Enability | 1. EXIT button of page should be Enable | 1. EXIT button of page is Enable | Pass | P0 | S0
| TC_46 | To verify EXIT button of page is functioning | Verify EXIT button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. click on EXIT button 6.Verify Functionality | 1. EXIT button of page should be Function and CLOSE the DOCUMENT page | 1. EXIT button of page is working and CLOSEING the page | Pass | P0 | S0
| TC_47 | To verify SEARCH button is enable | Verify SEARCH button is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. Click on SEARCH button 7. Verify Enability | 1. SEARCH button should be Enable | 1. SEARCH button is Enable | Pass | P0 | S2
| TC_48 | To verify SEARCH button is Functioning with valid data(+ VE TEST) | Verify SEARCH button is Functioning with valid data(+ VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. ENTER A VALID TADA 7. Click on SEARCH button 8. Verify functionality | By pressing search button result should be shown | By pressing search button result is showing | Fail | P1 | S1
| TC_49 | To verify SEARCH button is Functioning with invalid data(- VE TEST) | Verify SEARCH button is Functioning with invalid data(-VE TEST) |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. ENTER An INVALID TADA 7. Click on SEARCH button 8. Verify functionality | By pressing search button result should be shown as : No data available | By pressing search button result is showing as: No data available | Fail | P0 | S0
| TC_50 | To verify CHECK IN button of page is enable | Verify CHECK IN button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. click on CHECK IN button 7.Verify Enability | 1. CHECK IN button of page should be Enable | 1.CHECK IN button of page is Enable | Pass | P0 | S0
| TC_51 | To verify CHECK IN button of page is functioning | Verify CHECK IN button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. click on CHECK IN button 6.Verify Functionality | 1. CHECK IN button of page should be Function and select the document | 1. CHECK IN button of page Functions and select the document | Pass | P0 | S0
| TC_52 | To verify PREVIEW button of page is enable | Verify PREVIEW button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. click on PREVIEW button 7.Verify Enability | 1.PREVIEW button of page should be Enable | 1.PREVIEW button of page is Enable | Pass | P0 | S0
| TC_53 | To verify PREVIEW button of page is functioning | Verify PREVIEW button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. click on PREVIEW button 6.Verify Functionality | 1.PREVIEW button of page should be Function and preview the document | 1.PREVIEW button of page Functions and preview thedocument | Pass | P0 | S0
| TC_54 | To verify the PAGE LAYOUT IS as required | Verify the PAGE LAYOUT IS as required |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. click on PREVIEW button 6.Verify the page lay out | page out should be standard | page layout is not standard and presentable | Fail | P0 | S0
| TC_55 | To verify DOWNLOAD button of page is enable | Verify DOWNLOAD button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. Select a document 7. click on DOWNLOAD button 7.Verify Enability | 1.DOWNLOAD button of page should be Enable | 1.DOWNLOAD button of page is Enable | Pass | P0 | S0
| TC_56 | To verify DOWNLOAD button of page is functioning | Verify DOWNLOAD button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. select a document 6. click on DOWNLOAD button 6.Verify Functionality | 1.DOWNLOAD button of document should be Function and DOWNLOAD the document in user friendly format | 1.DOWNLOAD button downloads the document but it is not user friendly( document is in zip file) | Fail | P0 | S0
| TC_57 | To verify DELETE button of page is enable | Verify DELETE button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. click on DELETE button 7.Verify Enability | 1.DELETE button of page should be Enable | 1.DELETE button of page is Enable | Pass | P0 | S0
| TC_58 | To verify DELETE button of page is functioning | Verify DELETE button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. select a document 6.click on DELETE button 7.Verify Functionality | 1.DELETE button of page should be Function and delete the document | 1.DELETE button of page Functions and delete thedocument | Pass | P0 | S0
| TC_59 | To verify DELETE button of page is functioning(REGRESSION TEST) | Verify DELETE button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. select a document 6.click on DELETE button 7.Close the document page 8.search case id 9. check the document list 9.Verify deleted document is available or not | deleted document should be unavailable | selected deleted document is not available | Pass | P0 | S0
| TC_60 | To verify CANCEL button of page is enable | Verify CANCEL button of page is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on CASE ID LINK 6. click on CANCEL button 7.Verify Enability | 1.CANCEL button of page should be Enable | 1.CANCEL button of page is Enable | Pass | P0 | S0
| TC_61 | To verify CANCEL button of page is functioning | Verify CANCEL button of page is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on CASE ID LINK button 5. click on CANCEL button 6.Verify Functionality | 1.CANCEL button of page should be Function and exit the document page | 1.CANCEL button of page Functions and exit the document page | Pass | P0 | S0
main page | TC_62 | To verify UPLOAD button of document is enable | Verify UPLOAD button of document is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on UPLOAD 6.Verify Enability | 1.UPLOAD button of document should be Enable | 1.UPLOAD button of document is Enable | Pass | P0 | S0
| TC_63 | To verify UPLOAD button of document is functioning | Verify UPLOAD button of document is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on UPLOAD 6.brows document,select and uplod 7.Verify funnctionality | 1.UPLOAD button of document should be Function and upload the document | 1.UPLOAD button of document Functions and uploaded the document successfully | Pass | P0 | S0
| TC_64 | To verify EDIT button of document is enable | Verify UPLOAD button of document is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on EDIT button 6.Verify Enability | 1.EDIT button of document should be Enable | 1.EDIT button of document is not Enable | Fail | P0 | S0
| TC_65 | To verify EDIT button of document is functioning | Verify EDIT button of document is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on EDIT 6.Verify funnctionality | 1.EDIT button of document should be Function and allow to edit the document | 1.EDIT button of document does not Functions and allow to edit the document | Fail | P0 | S0
| TC_66 | To verify DELETE button of document is enable | Verify DELETE button of document is enable |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on DELETE button 6.Verify Enability | 1.DELETE button of document should be Enable | 1.DELETE button of document is Enable | Pass | P0 | S0
| TC_67 | To verify DELETE button of document is functioning | Verify DELETE button of document is functioning |  | 1. Open Browser 2. Enter URL: http://52.66.66.205:5069/# 3. Press ENTER key 4. Click on DOCUMENT button 5. Click on DELETE 6.Verify funnctionality | 1.DELETE button of document should be Function and open the cofirmation page | 1.DELETE button of document is deleting the document without any confirmation windows | Fail | P0 | S0
TC_68
TC_69
TC_70